## Sheet1
NO | Task | Details | Tanggal Mulai | Target Selesai | Tanggal Finish | Nama Dev | Debug | Solusi | Lama Waktu Handle
1 | Membuat Git Hub Repository |  | 2021-10-08 |  | 2021-11-10 | Amellia |  |  | 1 hari
2 | Menentukan Dataset |  | 2021-10-09 |  | 2021-11-11 | Melly |  |  | 1 hari
3 | Menentukan Artikel Utama |  | 2021-10-10 |  | 2021-11-12 | Amellia |  |  | 1 hari
4 | Membuat dan Mengisi File Sprint Project |  | 2021-10-11 |  | 2021-11-13 | Melly |  |  | 1 hari
5 | Preprocessing | Model 1 | 2021-10-25 |  | 2021-11-28 | Amellia |  |  | 3 hari
6 | Modelling | Model 1 | 2021-11-08 |  |  | Amellia
7 | Training Model | Model 1 | 2021-11-08 |  |  | Amellia
8 | Evaluasi Model | Model 1 | 2021-11-08 |  |  | Amellia
9 | Preprocessing | Model 2 | 2021-11-08 |  |  | Melly
10 | Modelling | Model 2 | 2021-10-25 |  | 2021-10-28 | Melly
11 | Training Model | Model 2 | 2021-11-08 |  |  | Melly
12 | Evaluasi Model | Model 2 | 2021-11-08 |  |  | Melly
13 | Melakukan proses preprocessing | splitting dataset menjadi (80% train, 19% validation, 1% test) | 2021-11-07
14 | Melakukan proses preprocessing | splitting dataset menjadi (80% train, 19% validation, 1% test) | 2021-11-07
15 | training beberapa skema model 1 | Menerapkan proses Convolution,Pooling,Dropout,BatchNormalization,variasi learning rate,100 epoch per model | 2021-11-08
16 | training beberapa skema model 2 | Menerapkan proses Convolution,Pooling,Dropout,BatchNormalization,variasi learning rate,100 epoch per model | 2021-11-08
17
18
19
20
21
22
23
24
25